## Product Backlog
Smart Home Automation System Testbed(Team 04)
Product Backlog
# | Formatted US ID | User Story | Story Point | Priority | Comments
Web browser GUI for SHAS
1 | US101 | Allow user(homeowner + family member) to log in SHAS by Web browser GUI | 3 | 1
3 | US103 | As a home owner, I want to monitor the status of all lights and turn on/off all light in the house | 3 | 2
4 | US104 | As a home owner, I want to dim/bright all light in the house | 3 | 3
5 | US105 | As a home owner, I want to monitor the status of all smart power outlets | 2 | 4
6 | US106 | As a home owner, I want to know which devices is plugged in the smart power outlets | 4 | 3
7 | US107 | As a home owner, I want to switch on/off all smart power outlets | 3 | 2
Sprinkler controls
8 | US202 | As a home owner, I want to monitor the status of Lawn sprinklers and turn on/off accordingly | 3 | 5
Water usage reports
9 | US301 | As a home owner, I want to see the water usage report by Day/Week/Month/Year | 4 | 6
Electricity usage reports
10 | US401 | As a home owner, I want to see the electricity usage report by Day/Week/Month/Year | 4 | 7
Security (police)
11 | US501 | SHAS should be have interface with Home Security System(HSS) | 5 | 8
12 | US502 | As a home owner, I want to be informed via phone call if security alarm is activated | 2 | 10
13 | US503 | HSS will automatically call police if alarm is activated | 2 | 9
HVAC (thermostat) for heating and cooling controls
14 | US601 | As a home owner, I want to monitor the status of HVAC | 4 | 13
15 | US602 | As a home owner, I want to turn on/off HVAC | 3 | 11
16 | US603 | As a home owner, I want to set the temperature of HVAC | 3 | 12
17 | US605 | As a home owner, I want to preset thermostat | 2 | 14
Fire, CO, gas alarms (fire dept)
18 | US701 | As a home owner, I want to monitor Fire Alarms | 5 | 15
19 | US702 | As a home owner, I want to monitor Carbon Monoxide Alarms | 5 | 15
20 | US703 | As a home owner, I want to monitor Gas Alarms | 5 | 15
21 | US704 | As a home owner, I want to be informed via phone call if Fire/CO/Gas alarms is activated | 2 | 17
22 | US705 | SHAC shall also notify current occupants of the situation and alert the appropriate authorities | 2 | 16
Window/door sensors
23 | US801 | As a home owner, I want to monitor the status of all windows/doors | 6 | 19
24 | US802 | As a home owner, I want to control(open/close) all windows/doors | 3 | 18
Energy Conservation
25 | US901 | As a home owner, I want swicth auto-mode on/off for HVAC | 3 | 21
26 | US902 | SHAS can automatically adjust HVAC to an preset temperature | 6 | 20
27 | US903 | As a home owner, I want switch auto-mode on/off for Light Control | 3 | 21
28 | US904 | SHAS can automatically adjust lighting whenever someone enters or exits a room, saving energy through minimal light usage | 6 | 20
29 | US905 | As a home owner, I want switch auto-mode on/off for Lawn sprinklers | 3 | 21
30 | US906 | SHAS can automatically enable the Lawn sprinklers based on the rain levels read by rain gauge | 6 | 20
SHAS Testbed
31 | US1001 | As a System Admin, I want to have all accesses which Home Owner has | 2 | 22
32 | US1002 | As a System Admin, I want to have capablity to simulate all appliances and devices in SHAS for testing | 7 | 23
33 | US1003 | As a System Admin, I should be able to simulate environment for testing | 6 | 24
Others
36 | US1101 | Allow user to log in SHAS by Smart Phone GUI | 10 | 25

## Questions
# | Questions | Answers
1 | Since we can see that there might be numeric data created and stored by SHAS system every day. Question is how long do we have to keep the data? For example, keep latest 2 years data (home owner), archive recent 5 years data (DBA), purge data 5 years before
2 | Can homeowner add/delete a device/family member?
3 | What happens when one of the appliance stops working ie how will the troubeshooting work?
4 | Do all the family members have the same login or each member should have separate login accounts?
5 | How should the system handle guests?
6 | Can we add a new appliance to the system?If Yes, who can add admin or even the home owner?